## Sheet1
Issue	State	Handler

Objects disappear when the viewport exceeds the geometric bounds of the old object	Unresolved
Objects clip through the floor when their vertices are altered	Unresolved
The center of mass of a modified mesh object remains unchanged by vertex alterations	Unresolved
Freed BGE data causes script failure – Keeping track of BGE objects in lists and dictionaries needs a more simplified and sound solution	Changes underway, wrote a function to remove objects from the dictionaries and lists before they are removed from the scene	Blastra
Due to files being constantly rewritten, SSD drives are not recommended for storing the game’s files	Solved, files are saved only with a manual command	Blastra
Basic Python HTTP Server is a severe security risk – recommended change to Flask	Solved, all actions use UDP now	Blastra
New Users must install Python3.4 – Newer available	Solved, external scripts no longer require Python 3.4	Blastra
New user server attempt shows no objects under some circumstances, but clients can join	Solved	Blastra
The host must load the scene from dbm before any clients may connect, failing to do this causes object ID indexing to fail	Unresolved
When a player connects to the scene, something about the Object IDs is amiss, temporarily all objects are refreshed into the list of transforming objects when a player connects	Solved	Blastra
Client’s view is jittery due to the lack of extrapolation	Solved	Blastra
HTTP threads are not shut down gracefully (possible security exploit)	Solved, all actions use UDP now	Blastra